## Sheet1
VEHICLE INSURANCE DETECTION SYSTEM --> Risk Management
| RISK | Event Type | Impact | Probability of Occurrence | Risk Rate | Mitigation Steps
1 | Personnel Shortfalls | Cost,fewer people | Severe | low | High | 1) Training on the progamming. 2) team building
2 | Unachievable Schedules | Schedule | Critical | medium | High | 1) Consult the Guide about the problem 2) proper schedule planning is required
3 | complexity of application | Performance | Critical | high | Medium | 1)Understanding The SRS 2)Proper documnetation of requiremnets
4 | gold plating | Performance | Severe | medium | Medium | 1)Usage of well developed software 2)Proper testing before giving to the user
5 | Inexperience in the problem domain | Cost Schedule Performance | Severe | high | High | 1)Experienced developers must be used for development of the given software 2)Proper survey of the problem domain